Study: Data Scientist Decision Making
Vinzent Müller
Oct 24th 2018

---
Overview
1. Subject of study: Out of Stock Dashboard
- Problem statement
- Process
- Conclusion

---
Problem: Out of Stock Items
- Lost revenue
- Negative user experience on website
- OKR goal of purchasing & PM department
  - Quantify possible reduction!
- Reportable to CEO

---
Problem: Out of Stock Items
- Involved Parties
  - Purchasing team
  - Product Management team
  - Operations & Logistics
Prelude
  1. First mention: JF with head of BI
  2. Personal meeting with head of purchasing
  3. Kick-off meeting with all parties

---
Kick-off
- Use information gathered in preliminary meetings to create case for suggested actions
- People are aware of the problem, but no quantification!

---
Kick-off
- Proposal: Power BI dashboard
  - Decide on list of metrics for first iteration
  - Per item: days OOS, lost NS, previous NS, delivery delay, # Orders
  - ‘appropriate visualisations’
  - presentable in one week
  - QA review sessions with purchasing
- Weekly incremental development
  - Goal #1: Inform OKR goals
  - Goal #2: Improve purchasing process

---
Review Sessions
- 1st session: review MVP
  - Minor glitches in calculations, some nominal data requested
  - Review session + 1D: product is usable
  - Ideas rolling in: “We have that metric in that file...”

---
Review Sessions
Final report: decision tree filter

---
Conclusion
- Explained OOS composition
  - Enables buyers to formulate processes for critical subgroups
- OKR goals fixed OOS reduction to 8 %
- Historized dashboard data allows tracking of improvements